## Strahlzeitplanung
|  |  | Quellen |  |  | SIS |  |  | #NAME? |  |  | #NAME? | Frühschicht bzw. ganzer Tag | [8 empty] | Spätschicht
KW | Datum |  | ECR | PEN | HSt | NS | FS | SS | SIS B-Exp. Shifts | Bemerkungen | Parasit | Tage ohne Exp. | Element | Ladung | Endenergie | Extraktionsart | Strahlziel | Intensität | Messsysteme | Daten zur Weiterverarbeitung | Sondereinstellungen | Element | Ladung | Endenergie | Extraktionsart | Strahlziel | Intensität | Messsysteme | Daten zur Weiterverarbeitung | Sondereinstellungen
27 | 2014-06-30 | Mo |  |  | N |  | Inbetriebnahme und SB56, Ondreka, Data Supply |  | #NAME?
27 | 2014-07-01 | Di |  |  |  |  | Inbetriebnahme und SB56, Ondreka, Data Supply |  | #NAME?
27 | 2014-07-02 | Mi |  |  |  |  | Bozyk, Inbetriebnahme Streak Kamera | Inbetriebnahme und SB56, Ondreka, Data Supply | #NAME?
27 | 2014-07-03 | Do | C |  |  |  | Sb55,Spiller,Ondreka, Closed Orbit Correction | SB62, Ondreka, Pyka, Slow Ext, Spill Structure | #NAME? |  |  | #NAME?
27 | 2014-07-04 | Fr |  |  |  |  | SB73,el-Hayek, Multiturninjektion optimieren | SB66, Spiller, High Current Booster | #NAME? |  |  | #NAME?
27 | 2014-07-05 | Sa | [6 empty] | #NAME? |  |  | #NAME?
27 | 2014-07-06 | So | [6 empty] | #NAME? |  |  | #NAME?
28 | 2014-07-07 | Mo |  | Au |  |  | SB45,Ningel, Commissioning H=2 | SB67, Ondreka, Spiller, Commissioning H=2/H=4 | #NAME? |  |  | #NAME?
28 | 2014-07-08 | Di |  |  |  |  | SB39, Ningel, Beam Phase Control Dual Harmonic | SB40, Nigel, Ondreka, Dual Harmonic Accel | #NAME? |  |  | #NAME?
28 | 2014-07-09 | Mi |  |  |  |  | SB48, H.-P. Ningel, S. Aumon, Logitudinal Intensity Effects DUAL RF 1 | SB51, Kornilov, Transverse Oscillations | #NAME? |  |  | #NAME?
28 | 2014-07-10 | Do |  |  |  |  | SB69, Franchetti, Boine, High Space Charge Operation 2 | SB66, Spiller et. Al. Booser Operation, H=2, TFS, Space Charge, Resonance 2 | #NAME? |  |  | #NAME?
28 | 2014-07-11 | Fr |  |  |  |  | SB63, Blell, TFS | SB32, Kauffmann, Chorniy, BPM Electronics 1 | #NAME? |  |  | #NAME?
28 | 2014-07-12 | Sa | [6 empty] | #NAME? |  |  | #NAME?
28 | 2014-07-13 | So | [6 empty] | #NAME? |  |  | #NAME?
29 | 2014-07-14 | Mo |  |  |  |  | SB62, Ondreka, Pyka, Slow KO? Ext, Spill Structure | SB38, Reeg, Chorniy, Logitudinal BD for SIS100 | #NAME? |  |  | #NAME?
29 | 2014-07-15 | Di |  |  |  |  | Sb72, Kowina, Pyka, KO extraction with BTF noise | SB38, Reeg, Chorniy, Logitudinal BD for SIS100 | #NAME? |  |  | #NAME?
29 | 2014-07-16 | Mi |  |  |  |  | SB23, Walasek-Höhne, Becek, Forck 2 | SB69, Franchetti, Boine, High Space Charge Operation 2 | #NAME? |  |  | #NAME?
29 | 2014-07-17 | Do | C |  | P |  |  |  | #NAME? |  |  | #NAME?
29 | 2014-07-18 | Fr | [6 empty] | #NAME? |  |  | #NAME?
29 | 2014-07-19 | Sa | [6 empty] | #NAME? |  |  | #NAME?
29 | 2014-07-20 | So | [6 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-21 | Mo | [6 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-22 | Di | [6 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-23 | Mi | [6 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-24 | Do | C | [5 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-25 | Fr | [6 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-26 | Sa | [6 empty] | #NAME? |  |  | #NAME?
30 | 2014-07-27 | So | [6 empty] | #NAME? |  |  | #NAME?
31 | 2014-07-28 | Mo | [9 empty] | 1
31 | 2014-07-29 | Di | [9 empty] | 1
31 | 2014-07-30 | Mi | [9 empty] | 1
31 | 2014-07-31 | Do | [9 empty] | 1
31 | 2014-08-01 | Fr | [9 empty] | 1
31 | 2014-08-02 | Sa | [9 empty] | 1
31 | 2014-08-03 | So | [9 empty] | 1
32 | 2014-08-04 | Mo | [9 empty] | 1
32 | 2014-08-05 | Di | [9 empty] | 1
32 | 2014-08-06 | Mi | [9 empty] | 1
32 | 2014-08-07 | Do |  | Au | Ni |  | SB29, Singh,Kowina, Tune Measurement | SB30, Giacomini, IPM | #NAME? |  |  | #NAME?
32 | 2014-08-08 | Fr |  |  |  |  | SB32, Kauffmann, Chorniy, BPM Electronics | SB33, Kowina, BPM Prototype | #NAME? |  |  | #NAME?
32 | 2014-08-09 | Sa | [9 empty] | 1
32 | 2014-08-10 | So | [9 empty] | 1
33 | 2014-08-11 | Mo |  |  |  |  | SB49, Appel, Optimization of MTI | SB37, Witthaus, SEM Grids | #NAME? |  |  | #NAME?
33 | 2014-08-12 | Di |  |  |  |  | SB51, Kornilov, Transvers Instabilities, Dual Harmonics | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  |  | #NAME?
33 | 2014-08-13 | Mi |  |  |  |  | SB38, Chorny, Longitudinal BD | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  |  | #NAME?
33 | 2014-08-14 | Do |  |  |  |  | SB51, Kornilov, Travers Instabilities with TFS, Dual Harmonic | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  |  | #NAME?
33 | 2014-08-15 | Fr |  |  |  |  | SB65, Bozyk,Cryogenic and warm desoption Experiments | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  |  | #NAME?
33 | 2014-08-16 | Sa | [9 empty] | 1
33 | 2014-08-17 | So | [9 empty] | 1
34 | 2014-08-18 | Mo | [6 empty] | #NAME? |  |  | #NAME?
34 | 2014-08-19 | Di |  |  | N |  |  | SB33, Kowina, BPM Prototype | #NAME? |  |  | #NAME?
34 | 2014-08-20 | Mi | [5 empty] | SB28, Hoffman et. Al., DAQ | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
34 | 2014-08-21 | Do | [5 empty] | SB50, Franchetti, Resonance Correction | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
34 | 2014-08-22 | Fr | [5 empty] | Sb53, Boine, Slow Extraction with High Intensity | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
34 | 2014-08-23 | Sa | [5 empty] | SB48,S. Aumon, H.-P. Ningel, Logitudinal Intensity Effects DUAL RF | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
34 | 2014-08-24 | So | [5 empty] | Sb51, Kornilov, Head Tail Instabilities | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-25 | Mo | [5 empty] | SB62, Ondreka, Spill Structure | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-26 | Di | [5 empty] | SB62, Ondreka, Spill Structure | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-27 | Mi |  | Xe |  |  |  | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-28 | Do | [5 empty] | SB59, Franchetti, High Space Charge | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-29 | Fr | [5 empty] | SB64, Spiller,Ondreka, 10 T/S | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-30 | Sa | [5 empty] | Sb53, Boine, Slow Extraction with High Intensity | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
35 | 2014-08-31 | So | [5 empty] | Sb53, Boine, Slow Extraction with High Intensity | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-01 | Mo | [5 empty] | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-02 | Di | [5 empty] | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-03 | Mi | [5 empty] | SB59, Franchetti, High Space Charge | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-04 | Do | [5 empty] | SB33, Kowina, BPM Prototype | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-05 | Fr | [5 empty] | SB62, Ondreka, Spill Structure | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-06 | Sa | [5 empty] | SB56, Ondreka, Data Supply | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
36 | 2014-09-07 | So | [5 empty] | SB40, Ningel, Dual Harmonic Acceleration | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
37 | 2014-09-08 | Mo | [5 empty] | SB62, Ondreka, Spill Structure | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
37 | 2014-09-09 | Di | [5 empty] | SB63, Blell, TFS | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
37 | 2014-09-10 | Mi |  |  |  |  | SB44, Ningel, Feedback Around Aplifier | Sb51, Kornilov, Head Tail Instabilities | #NAME? |  | Sb59, Spiller, Radon. Radiation Protection Mesurements | #NAME?
37 | 2014-09-11 | Do | Ca |  |  |  | SB61, Reiter,Lavrik, BLM Scaling | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  |  | #NAME?
37 | 2014-09-12 | Fr |  |  |  |  | SB28, Hoffman, Data Acquisition (FESA) | SB27, Reiter, Walasek-Höhne, Detector Tests HEBT | #NAME? |  |  | #NAME?
37 | 2014-09-13 | Sa |  |  | D |  |  |  | #NAME? |  |  | #NAME?
37 | 2014-09-14 | So | [6 empty] | #NAME? |  |  | #NAME?
38 | 2014-09-15 | Mo | [6 empty] | #NAME? |  |  | #NAME?
38 | 2014-09-16 | Di | [6 empty] | #NAME? |  |  | #NAME?
38 | 2014-09-17 | Mi |  |  | Xe | SB23, Walasek-Höhne, Becek, Forck | SB56, Data Supply, Bunch Merging | SB42, Ningel, Automatic Bunch Compressor | #NAME? | An diesen Tagen sind die Schichten normal verteilt |  | #NAME?
38 | 2014-09-18 | Do |  |  |  | SB27, Reiter, Walasek-Höhne, Becek, Forck | SB55, Ondreka, Closed Orbit Correction on Ramp | SB41, Ningel, Bunch Merging | #NAME? | An diesen Tagen sind die Schichten normal verteilt |  | #NAME?
38 | 2014-09-19 | Fr |  |  |  | SB23, Walasek-Höhne, Becek, Forck | SB66, Spiller, High Current Booster | Sb50, Franchetti, Resonance Correction | #NAME? | An diesen Tagen sind die Schichten normal verteilt |  | #NAME?
38 | 2014-09-20 | Sa |  |  |  |  | Sb51, Kornilov, Head Tail Instabilities | SB63, Blell, TFS | #NAME? |  |  | #NAME?
38 | 2014-09-21 | So |  |  |  |  | SB61, Reiter,Lavrik, BLM Scaling | SB23, Walasek-Höhne, Becek, Forck | #NAME? |  |  | #NAME?
39 | 2014-09-22 | Mo |  |  |  |  | SB45,Ningel, Commissioning H=2 | SB67, Ondreka, Spiller, Commissioning H=2/H=4 | #NAME?
39 | 2014-09-23 | Di |  |  |  |  | SB39, Ningel, Beam Phase Control Dual Harmonic | SB40, S. Aumon, H.-P. Ningel, Ondreka, Dual Harmonic Accel | #NAME?
39 | 2014-09-24 | Mi |  | Sm |  |  |  |  | #NAME?
39 | 2014-09-25 | Do | [6 empty] | #NAME?
39 | 2014-09-26 | Fr | [6 empty] | #NAME?
39 | 2014-09-27 | Sa | [6 empty] | #NAME?
39 | 2014-09-28 | So | [6 empty] | #NAME?
40 | 2014-09-29 | Mo | [6 empty] | #NAME?
40 | 2014-09-30 | Di | [6 empty] | #NAME?
40 | 2014-10-01 | Mi | [6 empty] | #NAME?
40 | 2014-10-02 | Do | [6 empty] | #NAME?
40 | 2014-10-03 | Fr | [6 empty] | #NAME?
40 | 2014-10-04 | Sa | [6 empty] | #NAME?
40 | 2014-10-05 | So | [6 empty] | #NAME?
41 | 2014-10-06 | Mo | [6 empty] | #NAME?
41 | 2014-10-07 | Di | [6 empty] | #NAME?
41 | 2014-10-08 | Mi | [6 empty] | #NAME?
41 | 2014-10-09 | Do | [6 empty] | #NAME?
41 | 2014-10-10 | Fr | [6 empty] | #NAME?
41 | 2014-10-11 | Sa | [6 empty] | #NAME?
41 | 2014-10-12 | So | [6 empty] | #NAME?
42 | 2014-10-13 | Mo |  |  | U |  | SB56, Ondreka, Data Supply | SB63, Blell, TFS | #NAME? | SB 65: few Shots U | SB65, Bozyk, Desportion
42 | 2014-10-14 | Di |  |  |  |  | SB54, Spiller. Uranium Low Charge State | SB61, BLM scaling | #NAME? | SB 65: few Shots U | SB65, Bozyk, Desportion
42 | 2014-10-15 | Mi |  |  |  |  | SB57,Spiller, Ondreka, Feldregelung | SB27, Reiter, Walasek-Höhne, Detector Tests HEBT | #NAME? | SB 65: few Shots U | SB65, Bozyk, Desportion
42 | 2014-10-16 | Do |  |  |  |  | SB40, Ningel, Dual Hamonic Operation | SB54, Spiller. Uranium Low Charge State | #NAME?
42 | 2014-10-17 | Fr |  |  |  |  | SB23, Walasek-Höhne, Becek, Forck | SB53, Boine, Slow Extraction with High Intensity | #NAME?
42 | 2014-10-18 | Sa |  |  |  |  | SB23, Walasek-Höhne, Becek, Forck | SB43, Ningel, Bunch to Bucket Transfer ESR, | #NAME? |  | SB60, Mustafin. Radiation Damage
42 | 2014-10-19 | So | [5 empty] | SB50, Franchetti, Resonance Correction | #NAME? |  | SB60, Mustafin. Radiation Damage
43 | 2014-10-20 | Mo | [5 empty] | SB000, Spezial, Spiller, Stadlmann, Ondreka, Barth, Hollinger,... | #NAME? | Einstellung vom zwei hochoptimierten Maschinen mit U73+, KO, Langsamer Extraktion und U28+ Booster, H=2, Dual RF. optimierte MTI in beiden Fällen, Unilac und Quellen Höchststrom, mit allen Erkenntnissen aus den Strahlzeiten | SB60, Mustafin. Radiation Damage
43 | 2014-10-21 | Di | [6 empty] | #NAME? |  | SB60, Mustafin. Radiation Damage
43 | 2014-10-22 | Mi | [6 empty] | #NAME? |  | SB60, Mustafin. Radiation Damage
43 | 2014-10-23 | Do | [6 empty] | #NAME? |  | SB60, Mustafin. Radiation Damage
43 | 2014-10-24 | Fr | [6 empty] | #NAME? |  | SB60, Mustafin. Radiation Damage
43 | 2014-10-25 | Sa | [5 empty] | SB60, Mustafin. Radiation Damage | #NAME? | SB 65: few Shots U | SB65, Bozyk, Desportion
43 | 2014-10-26 | So | [5 empty] | SB60, Mustafin. Radiation Damage | #NAME? | SB 65: few Shots U | SB65, Bozyk, Desportion
44 | 2014-10-27 | Mo | [6 empty] | #NAME?
44 | 2014-10-28 | Di | [6 empty] | #NAME?
44 | 2014-10-29 | Mi | [6 empty] | #NAME?
44 | 2014-10-30 | Do | [6 empty] | #NAME?
44 | 2014-10-31 | Fr | [6 empty] | #NAME?
44 | 2014-11-01 | Sa | [6 empty] | #NAME?
44 | 2014-11-02 | So | [6 empty] | #NAME?
Formulas:
KW = WEEKNUM([Datum],2)
Datum = [Datum, row above]+1

## Experimente SIS
Requests for Machine Experiments in Q3/ 2013 and Q1/ 2014 – STATE OF DISCUSSION
73
|  | Responsibilities |  | Experiment Informations | [12 empty] | Experiment Beam Parameters |  |  |  | Machine Parameters
|  |  |  | General |  |  |  | Administrative | [12 empty] | UNILAC |  | SIS
Nr. | EXPNR | Department | Respon-sible Person | Short Description of Experimental Topics | PSP-Code | Related FAIR System | Priority | Duration in Units of Shifts | Number of Campains | Contribu-tion Beam-time | Breaks Between Campains | Desired Calendar Week | Experimen-tal Area | Pulse-to-Pulse Sharing | Special Needs | Attendance of External Participants | Ion Species | Charge State | Energy/ Energy Range | Intensity/ Intensity Range | Pulse Length [ms] | Repetition Rate [Hz] | Rampe Rate [T/s] | Extraction Mode | Comment MK | Verbundforschung | verb shifts
7 | SB07 | LINAC | Groening/ Spiller | Life time measurements at SIS18 for medium charge states |  |  | 1 | 10 | 4 | 10 | > 1 month | start/ end of blocks | SIS | Excluded | foil instead of gas stripper |  | U | 28+ - 41+ | 11.4
23 | SB23 | SD | Walasek-Höhne, Forck et al. | Screen Investigations | 2.3.6 | Screens HEBT | 1 | 36 | 4 | 0 | yes |  | HTP | Possible | different ion beams (light, medium, heavy) and energies |  | N, Xe, U | [7 empty] | Sämtliche Schichtanforderungen der SD Abteilungen müssen gründlich hinterfragt und relativ zu den anderen Anforderungen reduziert werden
| SB23 | SD | Walasek-Höhne et al. | Optical Transition Radiation | 2.3.6 | HEBT BD | 1 |  | 3 | 0 | yes |  | HTP | Possible | tests at HTP and X2; high cur- rent; light, medium, heavy ions |  | N, Xe, U |  |  | >10^10 Teil- chen/ Puls
| SB23 | SD | Becker, Forck et al. | Beam Induced Flourescence | 2.3.6 | BIF HEBT | 1 |  | 4 | 0 | yes |  | HTP | Possible | different ion beams and energies |  | N, Xe, U
27 | SB27 | SD | Reiter, Walasek-Höhne et al. | Detector tests for HEBT (PDC, MWPC, PMT, SEM, RT&FCT, …) and pbar target (IC in air, OTR, BPM like IC, segmente IC, BLMI, …) | 2.9.6 | HEBT BD | 1 | 20 | 3 | 0 | yes |  | HTP | Possible | different ion beams & energies; high current; no HTA & C |  | N, Xe, U
28 | SB28 | SD | Hoffmann et al. | Data acqusition (FESA) | *.*.6 | DAQ all machines |  | 10 | 3 | 0 | yes |  |  | Possible | tests at different locations with various beam parameters |  | any
29 | SB29 | SD | Singh, Kowina, Forck et al. | Tune measurement - Commissioning of BI-instumentation, investigations with OBF | 2.8.6 | Tune meter SIS100, CR | 1 | 15 | 3 | 0 | yes |  | SIS | Possible | low to high current |  | N, Ar |  |  | >10^11 Ladungen
30 | SB30 | SD | Giacomini et al. | Ionization Profile Monitor SIS18 and ESR | 2.8.6 | IPM at SIS100, CR | 1 | 15 | 3 | 0 | yes |  | SIS | Possible | at SIS and ESR, different beams |  | any
32 | SB32 | SD | Kaufmann, Chorniy, Lang et al. | Beam Position Monitors electronics | 2.8.6 | BPM at SIS100, CR | 1 | 10 | 2 | 0 | yes |  | SIS | Possible |  |  | any
33 | SB33 | SD | Kowina, Reichert et al. | Beam Position Monitors SIS100 prototype | 2.8.6 | BPM at SIS100 | 1 | 10 | 2 | 0 | yes |  | HTP | Possible | prototype for SIS100 and HEBT |  | >= Ar |  |  | ~10^9 |  |  |  | schnell_1H4
36 | SB36 | SD | Schwickert, Kurian | Cryogenic Current Comparator tests | 2.3.6 | CCC at HEBT BD, CR | 2 | 2 | 2 | 0 | yes | 2013 | HTP | Possible | high current; 2days preparation in HTP; 1 month for He |  | N, Ar |  |  | 10nA |  |  |  | langsam
37 | SB37 | SD | Witthaus, Reeg et al. | Sem-Grid electronics tests | *.*.6 | BD for all machines | 1 | 10 | 3 | 0 | yes |  | HTP | Possible | tests at UNILAC & HEST |  | any
38 | SB38 | SD | Chorniy, Reeg et al. | Longitudinal BD for SIS100 (fast broad band current transformer) | 2.8.6 | SIS100, CR | 1 | 10 | 3 | 0 | yes |  | SIS | Possible |  |  | any |  |  | >10^8 Teilchen
39 | SB39 | HF | K.P. Ningel | Beam-Phase Control in stationary Dual-Harmonic Bucket | 2.8.4 | SIS100 | 1 | 2 | 2 | 2 | 4weeks | KW40, 2013 | SIS | Excluded | stable ion current |  | Ar | 18+ | <100MeV
40 | SB40 | HF | K.P. Ningel | Dual-Harmonic Operation with Acceleration | 2.8.4 | SIS100 | 1 | 2 | 2 | 2 | 4weeks | KW45, 2013 | SIS | Excluded | stable ion current |  | Ar | 18+ | <100MeV
42 | SB42 | HF | K.P. Ningel | Automation Bunch Compressor (with repect to varaible Energy/ Resonance frequency) | 2.8.4 | SIS100 | 1 | 2 | 2 | 0 | 4weeks | KW4, 2014 | SIS | Possible |  |  | Ar
41 | SB41 | HF | K.P. Ningel | Bunch-Merging with subsequent Bunch-Compression | 2.8.4 | SIS100 | 1 | 2 | 2 | 2 | 4weeks | KW48, 2013 | SIS | Excluded | stable ion current after 42 |  | Ar | 18+ | <100MeV
47 | SB47 | BP | S. Aumon | Optimization of the fast bunch compression | 2.8.1 | Bunch compressor | 1 | 2 | 2 | 2 |  |  | SIS | Excluded | bunch compressor cavity after/ together with 41 |  | Ar | 18 | 11.4-500 | 100000000000 |  |  |  | schnell_1H1 | Wird mehrfach angefordert und kann zusammengelegtw erden
43 | SB43 | HF | K.P. Ningel | Bunch-to-Bucket Transfer between SIS18 and ESR | 2.5.4 | SIS100/CR | 1 | 2 | 2 | 0 | 4weeks | KW8, 2014 | SIS | Possible |  |  | Ar | 18*
44 | SB44 | HF | K.P. Ningel | Optimization "Feedback around the Amplifier" | 2.8.4 | SIS100 | 1 | 2 | 2 | 0 | 4weeks | KW10, 2014 | SIS | Possible | high current |  | N | 7+ |  | >1x10E10
45 | SB45 | HF | K.P. Ningel | Commissioning and Optimization h=2-System |  | SIS18 | 1 | 6 | 3 | 6 |  | KW13, 2014 | SIS | Excluded | successfull basic commissioning |  | U | 28+
67 | SB67 | SY | Ondreka/ Spiller | Commissioning of dual harmonic operation H=2/ H=4 with beam |  |  |  | 6 | 1 | 6 |  |  | SIS | Excluded | high current, too, test of space charge correction in model |  | Ar
48 | SB48 | BP | H.-P. Ningel, S. Aumon | Longitudinal intensity effects in dual rf buckets | 2.8.1 | h=2 cavity | 1 | 2 | 2 | 2 |  |  | SIS | Excluded | dual rf operation after 45 |  | Ar | 18 | 11.4-500 | 100000000000 |  |  |  | schnell_1H4
49 | SB49 | BP | S. Appel | Optimization of the MTI for high intensity | 2.8.1 |  | 2 | 2 | 2 | 2 |  |  | SIS | Excluded |  |  | Ar | 18 | 11.4-500 | 100000000000 |  |  |  | schnell_1H4
50 | SB50 | BP | G. Franchetti | Resonance correction in SIS18 | 2.8.1 | correction elements | 1 | 2 | 2 | 2 |  |  | SIS | Excluded |  |  | Ar | 18 | 11.4- | 1000000000 |  |  |  | schnell_1H4
51 | SB51 | BP | V. Kornilov | Transverse coherent intensity effects: tune spectra and head-tail instabilities | 2.8.1 | tune measurements, transverse feedback systems | 2 | 2 | 2 | 2 |  |  | SIS | Excluded | dual rf operation, transverse feedback systems |  | Ar | 18 | 11.4- | 100000000000 |  |  |  | schnell_1H4
53 | SB53 | BP | Boine-Frankenheim | Slow Extraction with high intensity | 2.8 | SIS100 | 1 | 4 | 2 | 0 | yes | end2014 | SIS | Possible |  |  | N, Ar
54 | SB54 | SY | Spiller | Uranium Low Charge State Booster Operation | 2.14.11 | Link existing facility | 1 | 8 | 4 | 8 | yes |  | SIS | Excluded | ?; together with FRS-target? |  | U | 28+ | 200 | 50000000000
55 | SB55 | SY | Spiller/ Ondreka | Closed Orbit Correction with new PCs & CS, also during ramping | 2.14.11 | Link existing facility | 1 | 3 | 1 | 0 | yes |  | SIS | Possible | New PCs |  | any | any | full range | >5E8
56 | SB56 | SY | Ondreka | Tests of data supply also with different operation modes |  |  | 1 | 22 | 10 | 0 | yes |  | SIS | Possible |  |  | any | any | full range | >5E8
57 | SB57 | SY | Spiller/ Ondreka | Feldregelung | 2.14.11 | Link existing facility | 2 | 6 | 3 | 0 | yes | end 2014 | SIS | Possible | B train |  | any | any | full range | >5E8
59 | SB59 | SY | Spiller/ Radon | Measurements concerning radiation protection | 2.14.11 | Link existing facility | 1 | 6 | 3 | 0 | yes | end2014 | SIS | Possible |  |  | N | 7 | 2 GeV/u | 100000000000
60 | SB60 | SY | Mustafin | Radiation damage |  | SIS100 | 2 | 4 | 3 | 0 | yes | end2014 | SIS | Possible |  |  | U | 73 | 1 GeV/u | 4000000000
61 | SB61 | SD | Reiter/ Lavrik | BLM scaling, S03-Scraper will be used |  | SIS100 | 1 | 6 | 3 | 6 | yes | Start early 2013 | SIS | Excluded |  |  | N, Xe, U | TK | full range | max
62 | SB62 | SY | Ondreka | Optimisation of slow extraction, KO, micro spill struture, etc. |  | SIS100 | 1 | 6 | 3 | 0 | yes |  | SIS | Possible |  |  | any | any | full range | 1000000000
63 | SB63 | SY | Blell | TFS (Transversal Feedback System) commissioning |  | SIS100 | 1 | 5 | 3 | 0 | yes | end2014 | SIS | Possible |  |  | any | any | any | 1000000000
64 | SB64 | SY | Spiller/ Ondreka | Establishing of 10 T/s Ramps for SIS18 FAIR Operation | 2.14.11 | Link existing facility | 1 | 5 | 3 | 5 | yes | end2014 | SIS | Excluded |  |  | any | any | 12 Tm | 1000000000
66 | SB66 | SY | Spiller | Commissioning and optimization of SIS18 booster operation for FAIR | 2.14.11 | Link existing facility | 2 | 6 | 3 | 6 | yes | end2014 | SIS | Excluded | H=2, fast ramping available |  | U | div | div | div
65 | SB65 | SY | Bozyk | Crygenic and warm Desorption Experiments |  | FAIR relevant | 1 | 3
68 | SB68 | SY | Tennholt | Tests of pulsed plasma lens |  |  | 1 | 6 | 2
70 | SB70 | SY | Kornilov | Design optimization of SIS100 halo collimation |  | FAIR relevant |  | 1 | 1 |  |  |  | SIS | Excluded |  |  | U
69 | SB69 | BP | Franchetti, Boine | High Space Charge Operation
71 | SB71 | BP | Franchetti, Boine | Tune Scan
73 | SB73 | SP | Hayek | Multiturn Injection Optimisation |  | FAIR relevant
72 | SB72 | SD/SP | Kowina/Pyka | KO Extraction with BTF Noise
273
Note on I7: Dr. Wolfgang Bayer: 21?
Note on P5: Special Needs: - special measurement equiment - participation of further GSI departments/ groups - dependency on developments of others - special timing needs - special operating mode - ...
Note on S5: Charge State: If a special charge state is required, this information is required.