## Tabelle1
Count of TaskFinishDate | Spaltenbeschriftungen |  | GSI Residual Needs in der Vergangenheit
Zeilenbeschriftungen | in past | 2019/11 | ProjectName | TaskName | TaskStartDate | TaskStartYear | TaskStartMonth | PSPCode | ActivityCode | G-Residual Needs | G-Estimated Cost
SIS100 / SIS18 | 109 | 3 | 02_08_06_02 | Detector electro-mechanics costs | 2019-08-01 08:00 | 2019 | 8 | 2.8.6.2.1.1.1 | SZ.Z034 | 171800 | 171800
2.8 | 109 | 3 | 02_08_06_04 | Detector+Mechanics | 2019-08-15 08:00 | 2019 | 8 | 2.8.6.4.1.1 | SZ.Z012 | 85872 | 85872
2.8.6 - SIS100 Beam Instrumentation - Kowina; Piotr Dr. |  |  | 02_08_06_04 | DAQ slow readout | 2019-08-15 08:00 | 2019 | 8 | 2.8.6.4.1.6.1 | SZ.Z014 | 24850 | 24850
02_08_06_01 |  |  | 02_08_06_04 | SAT accepted PowCon (M10) | 2019-09-23 08:00 | 2019 | 9 | 2.8.6.4.1.1 | SZ.Z025 | 30309 | 30309
2.8.6.1.1.2 - DC Transformer Vacuum Chamber and Mechanics |  |  | 02_08_06_04 | documentation complete final PowCon | 2019-09-24 08:00 | 2019 | 9 | 2.8.6.4.1.1 | SZ.Z027 | 10103 | 10103
FAIR |  |  | 02_08_06_04 | SAT accepted Vakuum Kammer (M10) | 2019-09-20 17:00 | 2019 | 9 | 2.8.6.4.1.1 | SZ.Z026 | 62156.5 | 62156.5
S002.M4 | 1 |  | 02_08_06_05 | Miscellaneous Costs 2019 | 2019-05-29 08:00 | 2019 | 5 | 2.8.6.5 | SMC.AC2019 | 196011 | 196011
S002.M5 | 1 |  | 02_08_06_06 | Contract is signed (M4) | 2019-08-01 17:00 | 2019 | 8 | 2.8.6.6.1.6 | S002.M4 | 21042 | 21042
S002.M6 | 1 |  | 02_08_06_06 | Contract is signed (M4) | 2019-07-30 17:00 | 2019 | 7 | 2.8.6.6.2.6 | S002.M4 | 168087 | 168087
2.8.6.1.1.4 - DC Transformer Long Cables
FAIR
S002.M5 | 1
S002.M6 | 1 |  | FAIR Residual Needs in der Vergangenheit
S002.M7 | 1 |  | ProjectName | TaskName | TaskStartDate | TaskStartYear | TaskStartMonth | PSPCode | ActivityCode | F-Residual Needs | F-Estimated Cost
S003.MX1 | 1 |  | 02_08_06_05 | Purchase of HV Supply for BLMI | 2019-07-15 08:00 | 2019 | 7 | 2.8.6.5.1.5.1.2 | SZ.Z026 | 886800 | 886800
S004.M8 | 1 |  | 02_08_06_06 | [Merkposten Lambertson-Septum Screen] | 2019-09-30 08:00 | 2019 | 9 | 2.8.6.6.1.3.0 |  | 25000 | 25000
S005.M81 | 1 |  | 02_08_06_06 | Contract is signed (M4) | 2019-10-01 08:00 | 2019 | 10 | 2.8.6.6.1.2 | S002.M4 | 19000 | 19000
S005.M9 | 1 |  | 02_08_06_06 | Contract is signed (M4) | 2019-10-07 08:00 | 2019 | 10 | 2.8.6.6.2.2 | S002.M4 | 102000 | 102000
S006.M10 | 1 |  | 02_08_06_06 | Contract is signed (M4) | 2019-09-27 17:00 | 2019 | 9 | 2.8.6.6.1.1 | S002.M4 | 120500 | 120500
S006.M91 | 1 |  | 02_08_06_06 | Contract is signed (M4) for lambertson septum | 2019-10-01 08:00 | 2019 | 10 | 2.8.6.6.1.3.0 | S002.M4 | 25000 | 25000
S006.M92 | 1 |  | 02_08_06_06 | Contract is signed (M4) | 2019-07-30 17:00 | 2019 | 7 | 2.8.6.6.2.6.2 | S002.M4 | 5000 | 5000
2.8.6.1.2 - DC Transformer Novel System |  |  | 02_08_06_06 | Contract is signed (M4) | 2019-07-30 17:00 | 2019 | 7 | 2.8.6.6.2.5.2 | S002.M4 | 20000 | 20000
0 |  |  | 02_08_06_06 | Contract is signed (M4) | 2019-07-30 17:00 | 2019 | 7 | 2.8.6.6.2.3.2.2 | S002.M4 | 30000 | 30000
S005.M81 | 1
2.8.6.1.2.2 - DC Transformer Novel System Vacuum Chamber and Mechanics
FAIR
S004.M8 | 1
S005.M81 | 1
2.8.6.1.2.6 - DC Transformer Novel System Data Acquisition (per channel)
Tehnodrom
S005.M9 | 1
02_08_06_02
2.8.6.2.1.1 - Beam Position Monitor Detector
0
S006.M92 | 1
2.8.6.2.1.1.1 - Beam Position Monitor Pick-up
GSI
S005.M9 | 5
S006.M10 | 1 | 1
S006.M92 | 4
2.8.6.2.1.3.3 - Beam Position Monitor Other
GSI
S002.M4 | 1
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
S003.MX1 | 1
02_08_06_03_04
2.8.6.3.4.1 - Fast Current Transformer Detector
0
S002.M3 | 1
S002.M4 | 1
S004.M8 | 1
S005.M81 | 1
2.8.6.3.4.1.1 - Fast Current Transformer Ceramic Rings
FAIR
S002.M3 | 1
S002.M4 | 1
S002.M7 | 1
S003.MX1 | 1
S004.M8 | 1
S005.M81 | 1
02_08_06_05
2.8.6.5.1 - Beam Loss Monitor
0
S002.M6 | 1
S002.M7 | 1
2.8.6.5.1.5 - Beam Loss Monitor Additional equipment
0
S002.M6 | 1
S002.M7 | 1
2.8.6.5.1.5.1 - Beam Loss Monitor High-voltage Supply
Tehnodrom
S002.M6 | 1
S002.M7 | 1
2.8.6.5.1.6 - Beam Loss Monitor Data Acquisition (per channel)
Tehnodrom
S002.M6 | 1
S002.M7 | 1
02_08_06_06
2.8.6.2.1 - BPM Cold Sections
0
S002.M4 | 1
2.8.6.6.1 - Scintillation Screen
0
S002.M3 | 1
S005.M81 | 1
2.8.6.6.1.1 - Scintillation Screen Detector
FAIR
S002.M3 | 1
S002.M4 | 1
S003.MX1 | 1
S004.M8 | 1
S005.M81 | 1
2.8.6.6.1.2 - Scintillation Screen Vacuum Chamber
FAIR
S002.M4 | 1
2.8.6.6.1.3.0 - Scintillation Screen Mechanics
FAIR
S002.M4 | 1
2.8.6.6.1.4 - Scintillation Screen Long Cables and Electronics
FAIR
S002.M3 | 1
S002.M4 | 1
S003.MX1 | 1
S004.M8 | 1
S005.M81 | 1
2.8.6.6.2 - SEM-Grid
0
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
2.8.6.6.2.1 - SEM-Grid Detector
FAIR
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
2.8.6.6.2.2 - SEM-Grid Vacuum Chamber
FAIR
S002.M4 | 1
S005.M81 | 1
2.8.6.6.2.3 - SEM-Grid Mechanics
0
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
2.8.6.6.2.3.0 - SEM-Grid Mechanics
FAIR
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
2.8.6.6.2.4 - SEM-Grid Long Cables and Electronics
FAIR
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
2.8.6.6.2.5 - SEM-Grid Subsystems others
0
S002.M5 | 1
S002.M6 | 1
S002.M7 | 1
2.8.6.6.2.6 - SEM-Grid Data Acquisition (per channel)
GSI
S005.M9 | 1
S006.M91 | 1
S006.M92 |  | 1
2.8.6.6.3 - Faraday-Cup/Beam Stopper
0
S002.M6 | 1
2.8.6.6.3.1 - Faraday-Cup/Beam Stopper Detector
FAIR
S002.M5 | 1
S002.M6 | 1
2.8.6.6.3.2 - Faraday-Cup/Beam Stopper Vacuum Chamber
FAIR
S002.M4 | 1
S005.M81 | 1
2.8.6.6.3.3 - Faraday-Cup/Beam Stopper Mechanics
0
S002.M5 | 1
S002.M6 | 1
2.8.6.6.3.3.0 - Faraday-Cup/Beam Stopper Mechanics
FAIR
S002.M5 | 1
S002.M6 | 1
2.8.6.6.3.4 - Faraday-Cup/Beam Stopper Long Cables and Electronics, HV supply
FAIR
S002.M5 | 1
S002.M6 | 1
2.8.6.6.3.5 - Faraday-Cup/Beam Stopper Additional equipment
0
S002.M5 | 1
S002.M6 | 1
2.8.6.6.3.5.1 - void
0
S002.M5 | 1
S002.M6 | 1
2.8.6.6.3.6 - Faraday-Cup/Beam Stopper Data Acquisition (per channel)
GSI
S003.MX1 | 1
02_08_06_06_01
2.8.6.6.1.3 - Scintillation Screen Mechanics
0
S002.M7 | 1
2.8.6.6.1.3.2 - Scintillation Screen Pressurized air drive
Tehnodrom
S002.M7 | 1
2.8.6.6.2.3.2 - SEM-Grid Pressurized air drive
Tehnodrom
S002.M7 | 1
S003.MX1 | 1
2.8.6.6.3.3.2 - Faraday-Cup/Beam Stopper Pressurized air drive
Tehnodrom
S002.M7 | 1
S003.MX1 |  | 1
Gesamtergebnis | 109 | 3